## Project Timeline
Status | Item/To Do | Assigned to: | Due Date/Deadline | Status | Notes/Updates | January | Month (add as many months as you need) | Month | Day of Event | Post Event Follow up
Invitations and RSVP Management | Review initial list and add/subtract |  |  | Complete | Be intentional about focus on practitioners/funders/who else. Be specific about who we want to develop tools for
| List Finalized |  |  | Complete
| Gather feedback from Planning Group |  |  | Complete
| Event Invitation Designed |  |  | Complete
| First Invitation Sent (Date) |  |  | Complete |  |  | Send: Feb 9
| RSVP Management |  |  | Complete | Ongoing
Planning Group Meeting Management | Develop Meeting schedule and send meeting invites |  |  | Complete | 2x per month and weekly in the final weeks leading to event. Plan for 45 minutes and have a specific agenda and goals for each meeting
| Planning Committee agendas and materials |  |  | Complete
Event Communications (March/April): Communications will come from Megan | Develop communication schedule for Feb/March with links to Data Room |  |  | Complete
| Create event data room |  | 2024-03-01 | Complete | Will you create a digital data room so attendees have access to pre-reading materials?
| Outreach #1 |  | 2024-03-06 | Complete | Official Welcome, thank you. Includes goals and objectives + participant list
| Outreach #2 |  | 2024-03-13 | Complete | Will you send pre-reading in the form of relevant articles or research? Consider sending 2-3 weeks out from the event
| Outreach #3 |  | 2024-03-20 | Complete | Consider a pre-event survey? Send two weeks before the event if you can
| Outreach #4 | Jody & Megan | 2024-03-27 | Complete | Survey Reminder+ Final Logistics + Agenda with details, participant list, one more piece of reading (possibly social isolatino?), call to action. Send one week before the event
| Outreach #5 |  | April | Not yet started | Final reminder? Your planning team will decide how many times you want to reach out to attendees before the event
| Outreach #6 |  | April | Not yet started | Post event write up and next steps
Workshop Agenda Development | Finalize Event Goals/Objectives |  |  | Complete |  | x
| Determine Event Title |  | 2024-03-01 | Complete
| Decide on Speakers |  | 2024-03-15 | Complete
| Speaker Confirmations |  | 2024-03-15 | Complete | Completion goal: One month before your event
Event materials development - session by session | Pre-Event Survey |  | 2024-03-15 | Complete
| Finalize Ice Breaker Format (index cards and introductions) |  |  | Complete
| Final Agenda to share with attendees |  |  | Complete
| Develop Event Run of Show/Run Down |  |  | Complete | Begin this important task at least one month before the event and give yourself time to make changes
| Master Slide presentation to accompany Run of show |  |  | Complete
| Intro remarks for your hosts |  |  | Complete
| Case Studies: PPT Template for presenters |  |  | Complete
| Case Studies: Small Group Worksheets (SWOT format?) |  |  | Complete
| Case Studies: Guides for facilitators |  |  | Complete
| Ecosystem Mapping Worksheets (Domains + Worksheet + plain 11 x 17 paper) |  |  | Complete
| Assign attendees to breakouts - mix it up and dont stay with the same group each time | Megan |  | Complete
| Glosssary of Terms | Jody |  | Complete
Printed Materials for Event (Column B offers suggestions of the types of materials you may want to have printed for the event) | Name Tags at Registration |  |  | Complete
| Table Tent/Names |  |  | Complete
| Printed Agenda |  |  | Complete
| Seed packets will be included in folders |  |  | Complete
| Participant List |  |  | Complete
| Workshop Guiding Principles (modelled on IHI) |  |  | Complete
| Worksheets for Case Study Sessions |  |  | Complete
| Event Glossary |  |  | Complete
| AFE stickers (for folder) |  |  | Complete
| Event Title sticker (for folder) |  |  | Complete
| Worksheet for Ecosystem Mapping Exercise |  |  | Complete
| Domains sheet for Ecosystem Mapping Exercie |  |  | Complete
Complete
Attendee Gift/Take Home | Will you give your guests a small token of appreciation? |  |  | Complete |  |  |  | 2024-03-15
| Gift item ordered at least 6 weeks in advance if possible |  |  | Complete
A non-exhaustive list of supplies to consider having on hand for the event | Markers |  |  | Complete
| Pens |  |  | Complete
| Sticky notes: a variety of colors |  |  | Complete
| Regular sticky notes, multi colored (Brainstorm Poster Board Session) |  |  | Complete
| 3M post it easel pads - Extra Large |  |  | Complete
| Large markers - fat tip - multiple colors |  |  | Complete
| Index cards for Ice Breaker -- Have the cards waiting at tables. Plain cards |  |  | Complete
| Extra name tags just in case |  |  | Complete
| Notebooks |  |  | Complete
| Extra pens and markers |  |  | Complete
Event Logistics | Will you be offering breakfast and/or coffee? |  |  | Complete
| Event space secured |  |  | Complete
| Luncheon reserved if you are hosting? |  |  | Complete |  |  |  | 2024-03-01
| Water and snacks? |  |  | Complete |  |  |  | 2024-03-01
Will you be recording your event?
A/V needs lined up?

## Possible Event Titles
Possible Event Titles | Scaling Successful Collaborations: Creating an Age-Friendly Ecosystem that Delivers
Creative Disruption Leading to Harmonious Collaboration in the Age-Friendly Ecosystem
Synthesizing and harmonizing efforts across the Age-Friendly Ecosystem to deliver better outcomes for older adults
| The word "synthesize" means to combine two or more things to create something more complex. It involves integrating, blending, or fusing different elements to form a cohesive whole. In various contexts, such as medicine, research, or manufacturing, synthesizing is the process of bringing together components to generate new materials, products, or information. | Synthesize for our glossary There is also good languagein here for Terry and Nadine opening remarks and also closing remarks. Allude to great composers and orchestras - the sum of the parts. It we want better outcomes for oldr adults, we need to blend and fuse our efforts more harmoniously. (Better not more) | Simpler Language: Combining and coordinating different efforts Terry: focus on how groups harmonize and synthesize their efforts, rather than just adding to them
| Harmony : A consistent, orderly and pleasing arrangement or combination of parts/A state of agreement, accord or unity between people, ideas or things | Harmony for our Glossary
Harmony and Synthesis Across the Age-Friendly Ecosystem: Something action oriented
Harmony and Synthesis of Efforts across the Age-Friendly Ecosystem: But How?
| Harmony of Effort across the Age-Friendly Ecosystem: Collaboration that Works | Does this sound too woo woo?
Creating a Harmonious AFE that Delivers
Combining and coordinating different efforts